## Product Backlog(To-do)
Group Number | 12
Project Name: | Book-A-Bite
Description: | Make Reservations for Resturants Seemless | PRODUCT BACKLOG (TO-DO)
Team Members | Diego Lopez, Cameron Boydd, Marcel Newman, Cayden Renegar, Abrar Mian | [6 empty] | Sprint 1 |  |  |  | Sprint 2
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Assigned To | Comments
ST-0 | As a user, I want to be able to see available reservations using a scrollable list so that I can view all of them. | Add a view all avaiable times button when viewing a restuarant. Implement a card or text view thats scrollable, allowing users to view all available resersvation slots until a certain time frame. | Sprint 1 | [6 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) |  |  | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)
ST - 1 | As a parent, I need to reserve a table at a resturant for my kids birthday party so the whole family can eat together. | Fill out user information showing how many attendants will be booked for the table, and sort through our database to find the first available table that can fit enough kids. If none, return a "No available tables" message | Sprint 1 | 1st |  |  | 1 | 10 |  | 0.1 | #REF! | 10 |  | #REF! | #REF!
ST - 2 | As a waiter I need a way to view reservations so that I can prep the tables. | User can be shown a list of booked tables and times for the establishment | Sprint 1 | 8th |  |  | 3 | 5 |  | 0.6 | #REF! | 5 |  | #REF! | #REF!
ST - 3 | As a manager, I need to see how many reservations there are so I can get a sense of how much staff I will need. | The manager should be able to see the whole reservations list as well as the number of people for each reservation. | Sprint 1 | 9th |  |  | 3 | 8 |  | 0.375 | #REF! | 8 |  | #REF! | #REF!
ST - 4 | As a restuarant host, I need to be able to cancel any reservations as we seem fit as a right to our business | Add a cancellation button, that prompts a "reason for cancellation" message. Once cancelled, a notification is sent to teh customer who made the reservation | Sprint 1 | 10th |  |  | 5 | 8 |  | 0.625 | #REF! | 8 |  | #REF! | #REF!
ST - 5 | As a student, I want to be able to reserve a table after my night class | Add a filter option for the time of day you need a reservation. Make it to where it shows all available times, the times you want, or both. | Sprint 2 | 6th |  |  | 3 | 5 |  | 0.6 | #REF! | 5 |  | #REF! | #REF!
ST - 6 | As a bussiness person, I need to be able to hold a table for my important lunch meeting | Add an option that shows the peak business hours. Some users may want to go when it is quiter or less crowded | Sprint 2 | 11th |  |  | 3 | 10 |  | 0.3 | #REF! | 10 |  | #REF! | #REF!
ST - 7 | As a Moderator, I want our website database to be secure, so that the users passwords are safe. | Site encryption, SSO, is enabled. | Sprint 2 | 4rd |  |  | 3 | 15 |  | 0.2 | #REF! | 15 |  | #REF! | #REF!
ST - 8 | As a UNCC student I would like to implement a student fundraiser system | Implement a system for giving a percentage of money from table to fundraiser. Requirements are modeled after other resturant policies. | Sprint 2 | 12th |  |  | 8 | 5 |  | 1.6 | #REF! | 5 |  | #REF! | #REF!
ST - 9 | As a UNCC student, I would like the layout to be clean, so that I can easily navigate it. | Web Standards and Usability Guidelines from https://webstandards.hhs.gov/guidelines/ are implemented accuractely. | Sprint 2 | 3rd |  |  | 3 | 15 |  | 0.2 | #REF! | 15 |  | #REF! | #REF!
ST - 10 | As a UNCC student, I would like to be able to create an account, so I can save my preferences. | Profile page implemented | Sprint 2 | 5th |  |  | 3 | 15 |  | 0.2 | #REF! | 15 |  | #REF! | #REF!
ST - 11 | As a Moderator, I would like the page to contain a list of popular tables | Implement a table in the database to track them | Sprint 3 | 7th |  |  | 1 | 8 |  | 0.125 | #REF! | 8 |  | #REF! | #REF!
ST - 12 | As a Moderator, I want first time users to see a first time tutorial after signing up | Tutorial splashscreen after user creation | Sprint 3 | 2nd |  |  | 5 | 20 |  | 0.25 | #REF! | 20 |  | #REF! | #REF!

## Doing
Group Number | 12
Project Name:
Description: | DOING
Team Members
Story # | Card Front | Card Back | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Sprint Number | Priority | Assigned To | Comments
ST - 1 | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) | Sprint 1
ST - 11 | As a Moderator, I would like the page to contain a list of popular games | Implement a table in the dataase to track them | 1 | 1 |  | 1 | #DIV/0! | Sprint 3 | 7th
ST - 12 | As a Moderator, I first time users to see a first time tutorial after signing up | Tutorial splashscreen after user creation | 5 | 4 |  | 1.25 | #DIV/0! | Sprint 3 | 2nd
ST - 4
ST - 5
ST - 6
ST - 7
ST - 8
ST - 9
ST - 10
ST - 11
ST - 12

## Story Point Key
Story Point Key

## FInished User Stories
Story # | Card Front | Card Back
ST-0 | As a user, I want to be able to see available reservations using a scrollable list so that I can view all of them. | Add a view all avaiable times button when viewing a restuarant. Implement a card or text view thats scrollable, allowing users to view all available resersvation slots until a certain time frame.
ST - 1 | As a parent, I need to reserve a table at a resturant for my kids birthday party so the whole family can eat together. | Fill out user information showing how many attendants will be booked for the table, and sort through our database to find the first available table that can fit enough kids. If none, return a "No available tables" message
ST - 5 | As a student, I want to be able to reserve a table after my night class | Add a filter option for the time of day you need a reservation. Make it to where it shows all available times, the times you want, or both.
ST - 6 | As a bussiness person, I need to be able to hold a table for my important lunch meeting | Add an option that shows the peak business hours. Some users may want to go when it is quiter or less crowded
ST - 8 | As a UNCC student I would like to implement a student fundraiser system | Implement a system for giving a percentage of money from table to fundraiser. Requirements are modeled after other resturant policies.
ST - 9 | As a UNCC student, I would like the layout to be clean, so that I can easily navigate it. | Web Standards and Usability Guidelines from https://webstandards.hhs.gov/guidelines/ are implemented accuractely.
ST - 10 | As a UNCC student, I would like to be able to create an account, so I can save my preferences. | Profile page implemented